Shoal Creek Watershed Protection Plan (WPP) Development:

Timeline and Document Review Plan

Authored and Prepared by:

Nick Dornak, Director of Watershed Services

The Meadows Center for Water and the Environment

Prepared in cooperation with the Texas Commission on Environmental Quality

and the U.S. Environmental Protection Agency

Draft March 11, 2019





|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Projected Date for Completion** | **Title** | **Description of Activity** | **Project Quarter** | **Document Review Objective(s)** |
| COMPLETE | FINAL Data Acquisition QAPP | Quality Assurance | Q3 | n/a |
| COMPLETE | FINAL Mapping and Modeling QAPP | Quality Assurance | Q4 | n/a |
| COMPLETE | Collaborative Review of Existing Data, Information and Reports | WCR Development | Q4 | n/a |
| COMPLETE | 12/5/18 - Stakeholder Meeting, Working Groups | Stakeholder Engagement | Q6 | Stakeholder input on existing reports. WPP goals. Develop stakeholder workgroups for WPP development. |
| COMPLETE | Rough Draft Watershed Characterization Report for Stakeholder Review | WCR Development | Q6 | n/a |
| COMPLETE | 1/30/19 - Stakeholder Meeting, Working Groups | Stakeholder Engagement | Q6 | Review of WCR Rough Draft. Stakeholder workgroup meetings to define objectives and review modeling assumptions. |
| 2/28/19 | Draft Modeling Report | Modeling | Q6 | n/a |
| 3/31/19 | Draft Watershed Characterization Report | WCR Development | Q7 | n/a |
| 4/2/19 | Stakeholder Meeting, Working Groups | Stakeholder Engagement | Q7 | Review Draft Modeling Report and Draft WCR. Begin to draft workgroup reports. |
| 4/24/19 | Stakeholder Meeting, Working Groups | Stakeholder Engagement | Q7 | Review Draft WCR. Provide input on Element D (technical and financial assistance). Develop Draft Working Group Report. |
| 5/31/19 | FINAL Watershed Characterization Report | WCR Development | Q7 | n/a |
| Mid-June 2019 | Stakeholder Meeting | Stakeholder Engagement | Q8 | Stakeholder feedback on First Draft of WPP focusing on management measures. |
| 8/7/19 | Stakeholder Meeting, Working Groups | Stakeholder Engagement | Q8 | Stakeholder feedback on Second Draft of WPP – measures revised. Provide input on Element E (information/education component). Develop Second Draft of Working Group Report focusing on standards in place, areas for improvement and BMPs. |
| Mid-Sept. 2019 | Stakeholder Meeting | Stakeholder Engagement | Q9 | Stakeholder feedback on Third Draft of WPP – measures revised. Provide input on Elements F – I (implementation schedule, measurable milestones, load reduction criteria, monitoring) |
| 10/31/19 | Draft Elements D, E, F, G and H | WPP Development | Q9 | n/a |
| 10/31/19 | Rough Draft Watershed Protection Plan for Stakeholder Review | WPP Development | Q9 | n/a |
| 10/31/19 | FINAL Modeling Report | Modeling | Q9 | n/a |
| Mid-Nov. 2019 | Stakeholder Meeting, Working Groups | Stakeholder Engagement | Q9 | Working groups report back to stakeholders w/ FINAL Working Group Reports and comments on Draft WPP. |
| Mid-Nov. 2019 | FINAL Working Group Reports | Stakeholder Engagement | Q9 | n/a |
| 12/31/19 | Draft Element I | WPP Development | Q9 | n/a |
| Mid-Jan. 2020 | Stakeholder Meeting | Stakeholder Engagement | Q10 | Stakeholder review of WPP and comments. |
| 2/1/20 | Draft WPP (full for submission to TCEQ) | WPP Development | Q10 | n/a |
| Mid-Mar. 2020 | Stakeholder Meeting | Stakeholder Engagement | Q11 | Stakeholder review of WPP and comments. |
| 3/31/20 | Formal Stakeholder Approval of WPP | WPP Development | Q11 | n/a |
| 5/31/20 | FINAL WPP to EPA | WPP Development | Q11 | n/a |
| Late-July 2020 | Stakeholder Meeting | Stakeholder Engagement | Q12 | Stakeholder review of WPP and comments. |
| 8/31/20 | Response to All Comments | WPP Development | Q12 | n/a |